## Construction Project Timeline
Construction Project Management
PROJECT TITLE |  |  | START
|  |  | 2025-09-21 |  | PROJECT DURATION
PROJECT MANAGER |  |  | END |  | in days
|  |  | 2026-06-01 |  | 254
TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS KEY
Planning | Complete |  | 2025-09-21 | 2025-09-30 | 10 |  | Not Started
Demo Prep | Not Started |  | 2025-10-01 | 2025-10-06 | 6 |  | In Progress
Demolition | In Progress |  | 2025-10-06 | 2025-10-24 | 19 |  | Complete
Excavation | Complete |  | 2025-10-25 | 2025-10-29 | 5 |  | On Hold
Concrete | On Hold |  | 2025-11-01 | 2025-11-13 | 13 |  | Overdue
Pre backfill | Overdue |  | 2025-11-13 | 2025-11-15 | 3 |  | Needs Review
Framing | Needs Review |  | 2025-10-25 | 2025-12-05 | 42
Roof | In Progress |  | 2025-11-19 | 2025-12-10 | 22
Plumbing | In Progress |  | 2025-10-29 | 2025-12-09 | 42
Windows | On Hold |  | 2025-11-22 | 2025-12-15 | 24
HVAC | In Progress |  | 2025-11-29 | 2025-12-20 | 22
Electrical | In Progress |  | 2025-12-10 | 2025-12-22 | 13
A/V | Complete |  | 2025-12-10 | 2025-12-15 | 6
House wrap | Complete |  | 2025-12-27 | 2025-12-30 | 4
Insulation | In Progress |  | 2025-12-03 | 2025-12-21 | 19
Drywall | In Progress |  | 2026-01-03 | 2026-01-23 | 21
Exterior stone | In Progress |  | 2026-01-03 | 2026-01-17 | 15
Exterior case work | Not Started |  | 2026-01-04 | 2026-01-13 | 10
Laundry/furnace room flooring | In Progress |  | 2026-02-16 | 2026-03-11 | 24
Hardwoods | In Progress |  | 2026-01-19 | 2026-03-10 | 51
Tile | On Hold |  | 2026-02-03 | 2026-02-14 | 12
Cabinets | In Progress |  | 2026-01-18 | 2026-03-06 | 48
Plumbing -hang sinks | In Progress |  | 2026-02-16 | 2026-02-23 | 8
Interior doors | Complete |  | 2026-02-25 | 2026-03-09 | 13
Millwork | Complete |  | 2026-02-15 | 2026-02-17 | 3
Interior painting | In Progress |  | 2026-02-28 | 2026-04-14 | 46
Stone Counters | In Progress |  | 2026-03-21 | 2026-03-31 | 11
Schedule Buffer | In Progress |  | 2026-02-28 | 2026-03-10 | 11
Decks | In Progress |  | 2026-02-28 | 2026-03-18 | 19
Interior doors- hang & hardware | Complete |  | 2026-05-03 | 2026-05-13 | 11
Appliances | Complete |  | 2026-05-02 | 2026-05-03 | 2
Plumbing | In Progress |  | 2026-05-02 | 2026-05-05 | 4
Electrical | In Progress |  | 2026-05-03 | 2026-05-11 | 9
Bathroom Glass | In Progress |  | 2026-05-09 | 2026-05-13 | 5
Garage Door dress up | Not Started |  | 2026-05-13 | 2026-05-18 | 6
FINAL Inspections | In Progress |  | 2026-05-02 | 2026-05-02 | 1
Wrap up | In Progress |  | 2026-05-09 | 2026-06-05 | 28
House Cleaning | On Hold |  | 2026-05-29 | 2026-06-10 | 13
Complete | In Progress |  | 2026-06-10 | 2026-06-10 | 1

## BLANK - Project Timeline
CONSTRUCTION PROJECT TIMELINE TEMPLATE
PROJECT TITLE |  |  | START
PROJECT DURATION
PROJECT MANAGER |  |  | END |  | in days
TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS KEY
Planning | [6 empty] | Not Started
Demo Prep | [6 empty] | In Progress
Demolition | [6 empty] | Complete
Excavation | [6 empty] | On Hold
Concrete | [6 empty] | Overdue
Pre backfill | [6 empty] | Needs Review
Framing
Roof
Plumbing
Windows
HVAC
Electrical
A/V
House wrap
Insulation
Drywall
Exterior stone
Exterior case work
Laundry/furnace room flooring
Hardwoods
Tile
Cabinets
Plumbing -hang sinks
Interior doors
Millwork
Interior painting
Stone Counters
Schedule Buffer
Decks
Interior doors- hang & hardware
Appliances
Plumbing
Electrical
Bathroom Glass
Garage Door dress up
FINAL Inspections
Wrap up
House Cleaning
Complete
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.