## Simple Gantt Chart - EX
Simple Gantt Chart
PROJECT TITLE
PROJECT MANAGER
COMPANY NAME
DATE
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project Charter | Leon W | 2023-03-12 | 2023-03-15 | 3 | 100%
1.1.1 | Project Charter Revisions | Kylie R | 2023-03-15 | 2023-03-16 | 1 | 100%
1.2 | Research | Pete S | 2023-03-15 | 2023-03-21 | 6 | 90%
1.3 | Projections | Steve L | 2023-03-16 | 2023-03-22 | 6 | 40%
1.4 | Stakeholders | Allen W | 2023-03-17 | 2023-03-22 | 5 | 70%
1.5 | Guidelines | Malik M | 2023-03-18 | 2023-03-22 | 4 | 60%
1.6 | Project Initiation | Malik M | 2023-03-23 | 2023-03-23 |  | 50%
2 | Project Definition and Planning
2.1 | Scope and Goal Setting | Steve L | 2023-03-24 | 2023-03-28 | 4 | 5%
2.2 | Budget | Allen W | 2023-03-29 | 2023-04-02 | 4 | 30%
2.3 | Communication Plan | Malik M |  |  |  | 0%
2.4 | Risk Management | Malik M |  |  |  | 0%
3 | Project Launch and Execution
3.1 | Status and Tracking | Pete S |  |  |  | 0%
3.2 | KPIs | Leon W |  |  |  | 0%
3.2.1 | Monitoring | Kylie R |  |  |  | 0%
3.2.2 | Forecasts | Kylie R |  |  |  | 0%
3.3 | Project Updates | Pete S |  |  |  | 0%
3.3.1 | Chart Updates | Malik M |  |  |  | 0%
4 | Project Performance / Monitoring
4.1 | Project Objectives | Steve L |  |  |  | 0%
4.2 | Quality Deliverables | Allen W |  |  |  | 0%
4.3 | Effort and Cost Tracking | Malik M |  |  |  | 0%
4.4 | Project Performance | Malik M |  |  |  | 0%

## Simple Gantt Chart - BLANK
SIMPLE GANTT CHART
PROJECT TITLE
PROJECT MANAGER
COMPANY NAME
DATE
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project Charter |  |  |  |  | 100%
1.1.1 | Project Charter Revisions |  |  |  |  | 0%
1.2 | Research |  |  |  |  | 0%
1.3 | Projections |  |  |  |  | 0%
1.4 | Stakeholders |  |  |  |  | 0%
1.5 | Guidelines |  |  |  |  | 0%
1.6 | Project Initiation |  |  |  |  | 0%
2 | Project Definition and Planning
2.1 | Scope & Goal Setting |  |  |  |  | 0%
2.2 | Budget |  |  |  |  | 0%
2.3 | Communication Plan |  |  |  |  | 0%
2.4 | Risk Management |  |  |  |  | 0%
3 | Project Launch and Execution
3.1 | Status & Tracking |  |  |  |  | 0%
3.2 | KPIs |  |  |  |  | 0%
3.2.1 | Monitoring |  |  |  |  | 0%
3.2.2 | Forecasts |  |  |  |  | 0%
3.3 | Project Updates |  |  |  |  | 0%
3.3.1 | Chart Updates |  |  |  |  | 0%
4 | Project Performance / Monitoring
4.1 | Project Objectives |  |  |  |  | 0%
4.2 | Quality Deliverables |  |  |  |  | 0%
4.3 | Effort and Cost Tracking |  |  |  |  | 0%
4.4 | Project Performance |  |  |  |  | 0%

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.