## EXAMPLE - RACI Matrix
Simple Raci Matrix
|  |  | Project Sponsor | CPO | Director | Role 4 | Role 5 | Project Manager | Operations Engineer | Quality Assurance | Developer | Role 5 | Consultant | Customer Service | Role 3 | Role 4 | Role 5 | Role 1 | Role 2 | Role 3 | Role 4 | Role 5
PRIORITY | STATUS | PROJECT DELIVERABLE / ACTIVITY | Project Leadership |  |  |  |  | Project Team Members |  |  |  |  | Additional Resources |  | Role 1: Other
PHASE 1
Low | In Progress | Request Review by PMO |  | R |  |  |  | R | A |  | C
Medium | Complete | Submit Project Request | [5 empty] | R | bar: Role 2
High | Needs Review | Research Solution | I |  |  |  |  | A | A | A | C | bar: Role 3; Role 1
| Approved | Develop Business Case | [5 empty] | R | bar: Role 2
Not Started
Overdue
On Hold
PHASE 2
|  | Create Project Charter | C | C |  |  |  | R | C | C | C | bar: Role 3; Role 1
|  | Create Schedule | I | I | I | I |  | R | C | C | C | C | C | C | bar: Role 3; Role 1 to Role 2
|  | Create Additional Plans as Required | I | I | I |  |  | R |  |  |  | I | I | I | bar: Role 3; Role 1 to Role 2
PHASE 3
|  | Build Deliverables | C | C | C | C |  |  | R | R | R | R | A | bar: Role 1
|  | Create Status Report | I | I | I | I |  | A | A | A | A | bar: Role 1 to Role 2
PHASE 4
|  | Perform Change Management |  | C | C | C |  | R | A | A | A | bar: Role 1 to Role 2
PHASE 5
|  | Create Lessons Learned | C | C | C | C |  | R | C | C | C | C | C | C | bar: Role 3; Role 1 to Role 2
|  | Create Project Closure Report | I | I | I | I |  | A | I | I | I | I | I | I | bar: Role 3; Role 2
RESPONSIBLE
ACCOUNTABLE
CONSULTED
INFORMED

## BLANK - RACI Matrix
SIMPLE RACI MATRIX
|  |  | Project Sponsor | CPO | Director | Role 4 | Role 5 | Project Manager | Operations Engineer | Quality Assurance | Developer | Role 5 | Consultant | Customer Service | Role 3 | Role 4 | Role 5 | Role 1 | Role 2 | Role 3 | Role 4 | Role 5
PRIORITY | STATUS | PROJECT DELIVERABLE / ACTIVITY | Project Leadership |  |  |  |  | Project Team Members |  |  |  |  | Additional Resources |  | Role 1: Other
PHASE 1
Low | Complete | Request Review by PMO | R
Medium | In Progress | Submit Project Request |  | A
High | Needs Review | Research Solution |  |  | C
| Approved | Develop Business Case |  |  |  | I
Not Started
Overdue
On Hold
PHASE 2
Create Project Charter
Create Schedule
Create Additional Plans as Required
PHASE 3
Build Deliverables
Create Status Report
PHASE 4
Perform Change Management
PHASE 5
Create Lessons Learned
Create Project Closure Report
RESPONSIBLE
ACCOUNTABLE
CONSULTED
INFORMED

## Dropdown Keys - Do Not Delete -
RACI DROPDOWN KEYS
– DO NOT DELETE –
| RACI KEY | PRIORITY | STATUS
R | Responsible | Low | Not Started
A | Accountable | Medium | In Progress
C | Consulted | High | Complete
I | Informed |  | Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.